## Sheet1
Project Description: |  |  |  | Possible extra features to include:
We intend to make a freezer buddy app. |  |  |  | * AR implementation
The app should help you to keep track of items in your freezer. |  |  |  | * Facebook connection
You should have the possibility to add items and the app |  |  |  | * Photo possibility
should notify you when the items are close to their expiration date. |  |  |  | * Tablet support
Information should be saved naturally so the app remembers what item |  |  |  | * Google ads
you have stored. This will be done either via local file management,
a database connection, or a combination of both.
Our target group will mainly be senior citizens, so clarity and
simplicity is of the essence. | [5 empty] | Tasks to be implemented / investigated:
[5 empty] | Assigned | Task number | Task Description
Student name | Task list | Min time | Approx. Time | Max time | P | #1 | Implement BottomNavigationActivity + Toolbar menu (Fragments + activity on clicks)
[5 empty] | M | #2 | Implement usage / permissions of camera
Patric | 1 | 3 | 6 | 15 | P | #3 | Implement notifications
| 5 | 4 | 16 | 32 | A | #4 | Design buttons / icons
| 16 | 8 | 32 | 58 | P | #5 | Investigate read / write file I/O
| 15 | 8 | 40 | 64 | M | #6 | Livedata/Viewmodel implementation to pass data between fragments / activities
| 3 | 3 | 8 | 16 | A | #7 | Save data on screen rotation / app pause / app destroy
[5 empty] | N | #8 | Investigate possible Firebase implementation with login
Patric total | All tasks total |  | 102h |  | M | #9 | Investigate AR possibilities
[5 empty] | M | #10 | Implement possibility to add items to freezer, file / database
[5 empty] | M | #11 | Investigate possibility to display items in certain priorities
[5 empty] | N | #12 | Investigate Google Ads implementation
Niklas | 8 | 8 | 32 | 48 | N | #13 | Possibility to change date format / language
| 18 | 8 | 24 | 40 | A | #14 | Possibility to add items with voice-to-text
| 12 | 8 | 32 | 48 | P | #15 | Investigate multi-threading for when adding items to database (possibly other situations)
| 17 | 4 | 8 | 24 | P | #16 | Implement one or more Jetpack composite functions for some views
| 13 | 2 | 6 | 12 | N | #17 | Weekly update notification in order to plan ahead
[5 empty] | N | #18 | Investigate other possible database implementations (local or remote)
Niklas total | All tasks total |  | 102h |  | A | #19 | Implement proper lifecycle management
[5 empty] | Task number | Task Description |  |  | Approx. Time
[5 empty] | #20 | Individual idea planning |  |  | 3,5h
Mattias | 6 | 8 | 16 | 40 | #21 | Collective meeting #1 |  |  | 2h
| 9 | 12 | 32 | 56 | #22 | Collective meeting #2 |  |  | 2h
| 2 | 8 | 32 | 40 | #23 | Collective meeting #3 |  |  | 2h
| 10 | 4 | 16 | 32 | #24 | Collective meeting #4 |  |  | 2h
| 11 | 3 | 6 | 12 | #25 | Project start meeting |  |  | 0.5h
[5 empty] | #26 | Project help #1 |  |  | 1,5h
Mattias total | All tasks total |  | 102h |  | #27 | Project help #2 |  |  | 1,5h
[5 empty] | #28 | Project help #3 |  |  | 1,5h
[5 empty] | #29 | Project help #4 |  |  | 1,5h
[8 empty] | Sum: | 18h
Axel | 4 | 16 | 32 | 64
| 7 | 8 | 16 | 32
| 14 | 24 | 32 | 56
| 19 | 10 | 22 | 36
[5 empty] | Total sum for all participants: | 120h
Axel total | All tasks total |  | 102h